## WEEKLY REPORT
Weekly Project Status Report
5170 Dave Robbins Way
Lakeland FL
start up
|  | HD Project Manager: | Perri Gardner | Contract Start Date: | 2018-03-05
|  |  |  | Actual Start Date: | 2018-03-05
|  | General Contractor: | Hanna Design Group | Planned Completion Date: | 2018-07-06
|  | GC Project Manager: | Jeff Mrnak | Actual Completion Date:
|  | GC Superintendent: | Tim West | HD Setup Date:
|  | Architect Rep: | KC Pavik | HD Setup Coordinator:
|  | Civil Design Rep: | Chris Blurton | Office Open Date:
ACCOMPLISHED THIS WEEK:
1 | steel completed ane inspected
2 | poured back concrete @ all collumns
3 | started electrical rough overhead
4 | started exterior framing
5 | completed all curbs and HVAC rough
6 | received ist brick delivery
PLANNED FOR NEXT WEEK: |  |  | 2018-05-14
1 | exterior wall framing
2 | rough electric exterior walls
3
4
5
6
OUTSTANDING RFI'S/ISSUES/CHANGE ORDERS:
1
2
3
4
5
OWNER COORDINATION ITEMS:
(Input information below as applicable during the construction process of when items are desired.)
1 | UTILITY COMPANIES: |  | Need account numbers for all final utilities
| ELECTRIC |  | Lakeland electric
GAS
WATER / SEWER
2 | FLOORING DELIVERY:
3 | TILE DELIVERY:
4 | FLOORING DELIVERY:
5 | LIGHTING DELIVERY:
6 | CABINETRY DELIVERY:
7 | SCHEIN INSTALL:
8 | PUNCH WALK THRU:
NOTES:
& INCLUDE SNAPSHOT OF PROJECT SCHEDULE