## WEEKLY REPORT
Weekly Project Status Report
5170 Dave Robbins Way
Lakeland FL
start up
|  | HD Project Manager: | Perri Gardner | Contract Start Date: | 2018-03-05
|  |  |  | Actual Start Date: | 2018-03-05
|  | General Contractor: | Hanna Design Group | Planned Completion Date: | 2018-07-06
|  | GC Project Manager: | Jeff Mrnak | Actual Completion Date:
|  | GC Superintendent: | Tim West | HD Setup Date:
|  | Architect Rep: | KC Pavik | HD Setup Coordinator:
|  | Civil Design Rep: | Chris Blurton | Office Open Date:
ACCOMPLISHED THIS WEEK:
1 | framed, sheeted and inspected 3 main exterior walls. Raedy for masonry
2 | Started masonry back wall. Received 2cd and 3rd load of brick
3 | rough electrical in exterior walls for mason completed
4 | rough electric interior walls continued
5 | interior framing 60 % completed
6 | started plumbing wall rough
PLANNED FOR NEXT WEEK: |  |  | 2018-05-28
1 | Monday HOLIDAY
2 | Continue masonry
3 | continue interior framing and backing
4 | continue exterior framing
5 | continue rough walls electric
6 | continue rough wall plumbing
OUTSTANDING RFI'S/ISSUES/CHANGE ORDERS:
1
2
3
4
5
OWNER COORDINATION ITEMS:
(Input information below as applicable during the construction process of when items are desired.)
1 | UTILITY COMPANIES: |  | Need account numbers for all final utilities
| ELECTRIC |  | Lakeland electric
GAS
WATER / SEWER
2 | FLOORING DELIVERY:
3 | TILE DELIVERY: |  | need 2cd week of June
4 | FLOORING DELIVERY: |  | need 2cd week of June
5 | LIGHTING DELIVERY: |  | scheduled 1st week of June
6 | CABINETRY DELIVERY: |  | scheduled 3rd week of June
7 | SCHEIN INSTALL: |  | TBD
8 | PUNCH WALK THRU:
NOTES:
& INCLUDE SNAPSHOT OF PROJECT SCHEDULE